## Worksheet
Startup Planning - Daily Project Tracker (Daily)
Task ID | Task Name | Assigned To | Due Date | Status | Daily Progress (%) | Notes / Updates
T001 | Market Research & Validation | Alice Johnson | 2025-04-05 | In Progress | 75% | Completed survey phase; analyzing feedback.
T002 | Business Model Development | Bob Smith | 2025-04-06 | To Do | 15% | Scheduled for discussion in team meeting.
T003 | Prototype Design (MVP) | Carla Diaz | 2025-04-10 | In Progress | 60% | Figma wireframes reviewed and approved.
T004 | Seed Funding Pitch Deck | Daniel Kim | 2025-04-15 | In Progress | 35% | Funding metrics updated with new projections.
T005 | Legal Structure Setup | Eva Patel | 2025-04-12 | Completed | 100% | Limited Liability Company (LLC) registered.
Last Updated: April 4, 2025 ¦ Daily Update