## Worksheet
Task | Assignee | Status | Start Date | Due Date | Progress (%)
Develop MVP Concept | Alice Johnson | In Progress | 2023-10-01 | 2023-10-15 | 75
Create Business Model Canvas | Bob Smith | To Do | 2023-10-02 | 2023-10-10 | 0
Conduct Market Research | Carol Davis | In Progress | 2023-10-03 | 2023-10-18 | 60
Build Prototype Interface | Daniel Lee | In Progress | 2023-10-05 | 2023-10-25 | 45
Finalize Funding Pitch Deck | Elena Martinez | To Do | 2023-10-06 | 2023-10-30 | 5
Secure First 5 Pilot Customers | Frank Wilson | Not Started | 2023-10-08 | 2023-10-31 | 0