## Worksheet
Startup Planning - Project Tracker (Financial View)
Track key financial milestones and project progress in real-time
Project ID | Project Name | Status | Planned Start Date | Planned End Date | Budget (USD) | Actual Spend (USD) | Budget Variance (USD) | % of Budget Used
PJ001 | Product Development MVP | In Progress | 2024-01-15 | 2024-06-30 | $350,000 | $187,543 | $162,457 (Under) | 53.6%
PJ002 | Market Launch Campaign | In Progress | 2024-03-01 | 2024-11-30 | $550,000 | $98,765 | $451,235 (Under) | 17.9%
PJ003 | Team Expansion & Hiring | On Hold | 2024-04-15 | 2024-12-31 | $650,000 | $78,999 | $571,001 (Under) | 12.1%
PJ004 | Infrastructure & Cloud Setup | Completed | 2023-12-01 | 2024-05-15 | $85,000 | $83,976 | $1,024 (Under) | 98.8%
PJ005 | Legal & IP Registration | Completed | 2024-01-10 | 2024-03-31 | $38,500 | $37,695 | $805 (Under) | 97.9%
PJ006 | Customer Acquisition Pilot | In Progress | 2024-05-15 | 2024-11-30 | $78,900 | $34,678 | $44,222 (Under) | 43.9%
Financial Summary
Total Budget Allocated:$2,458,400
Total Actual Spend:$519,656
Total Budget Variance (Remaining):$1,938,744 (Under)
Average % of Budget Used Across Projects:37.2%