## Worksheet
Startup Planning - Monthly Project Tracker
Project ID | Project Name | Phase | Status | Owner | Start Date | End Date | Budget (USD) | Milestones Achieved (%)
SP-001 | Product Development MVP | Development | In Progress | Jane Smith | 2024-01-15 | 2024-03-31 | $85,000 | 65%
SP-002 | Market Research & Validation | Research | Completed | Mike Johnson | 2024-01-01 | 2024-01-31 | $15,000 | 100%
SP-003 | Seed Funding Campaign | Fundraising | In Progress | Lisa Wong | 2024-02-15 | 2024-04-30 | $150,000 | 38%
SP-004 | Team Recruitment | Hiring | In Progress | David Lee | 2024-01-10 | 2024-03-15 | $35,000 | 75%
SP-005 | Brand Identity & Website Launch | Marketing | Pending Start | Sarah Patel | 2024-03-15 | 2024-05-31 | $45,000 | 5%
Total Projects: |  |  | 5
Avg. Progress: |  |  | 59.8%