## Worksheet
Startup Planning - Project Tracker (Multi-Page)
Project Name: _________________________ ¦ Start Date: ___________ ¦ End Date: ___________
Phase 1: Concept & Validation
Task ID | Task Description | Owner | Status | Start Date | End Date | % Complete
T001 | Define core problem & solution idea | CEO/Founder | In Progress | 2024-01-15 | 2024-01-25 | 65%
T002 | Conduct market research & competitor analysis | MKT Lead | To Do | 2024-01-26 | 2024-01-31 | 5%
T003 | Validate idea with 5+ target users (survey) | User Researcher | To Do | 2024-02-01 | 2024-02-15 | 1%
Key Milestones
- Finalize product concept: 2024-01-31 - User validation completed: 2024-02-15
Phase 2: MVP Development
Task ID | Task Description | Owner | Status | Start Date | End Date | % Complete
Product Development Tasks (Frontend)
T101 | Wireframe UI/UX design (Figma) | UI/UX Designer | In Progress | 2024-02-16 | 2024-03-15 | 75%
T102 | Develop core frontend components (React) | Frontend Dev | To Do | 2024-03-16 | 2024-05-15 | 8%
Product Development Tasks (Backend)
T103 | Design database schema & API endpoints | Backend Dev | In Progress | 2024-02-16 | 2024-03-15 | 85%
Testing & QA
T104 | Unit and integration testing (automated) | QA Engineer | To Do | 2024-05-16 | 2024-06-15 | 3%
Key Milestones
- MVP wireframes approved: 2024-03-15 - Core backend ready: 2024-03-15 - Frontend development complete: 2024-05-15
Phase 3: Launch Preparation
Task ID | Task Description | Owner | Status | Start Date | End Date | % Complete
Marketing & Sales Planning
T201 | Create brand identity (logo, tone, messaging) | Marketing Lead | In Progress | 2024-03-16 | 2024-04-15
Launch Campaigns (Digital & PR)
T202 | Build landing page & pre-launch signup funnel | Marketing/Dev Lead | To Do | 2024-05-16 | 2024-6-15
Operational Setup & Legal
T203 | Register business entity & obtain necessary licenses | Legal/COO | To Do | 2024-04-16 | 2024-05-15
Team & Budget Management
T204 | Finalize team roles & onboarding plan (if hiring) | HR/CEO | To Do | 2024-05-16 | 2024-6-30
Key Milestones
- Brand identity approved: 2024-04-15 - Legal foundation established: 2024-05-15 - Pre-launch campaign live: 2024-6-15
Phase 4: Go-Live & Post-Launch
Task ID | Task Description | Owner | Status | Start Date | End Date
Go-Live Activities
T301 | Deploy MVP to production (CI/CD) | DevOps Lead | To Do | 2024-06-16 | 2024-6-30
Customer Onboarding & Feedback Loop
T302 | Collect initial user feedback (first 50 customers) | User Experience Lead | To Do | 2024-07-01 | 2024-7-31
Post-Launch Roadmap Planning
T303 | Review performance metrics & define Q4 feature roadmap | Product Manager | To Do | 2024-08-01 | 2024-8-31
Key Milestones
- MVP launched to public: 2024-06-30 - First 50 customers onboarded: 2024-7-31 - Q4 roadmap approved: 2024-8-31
Startup Planning - Project Tracker ¦ Page 2 of 2 ¦ Updated: