## Worksheet
Startup Planning - Project Tracker
Task ID | Project Phase | Task Name | Description | Assigned To | Start Date | Due Date
#SP001 | Ideation & Research | Market Research Analysis | Conduct comprehensive research on target market, competition, and user needs. | Jane Doe | 2024-04-01 | Pending
#SP002 | Ideation & Research | Competitor Analysis Report | Compile detailed analysis of direct and indirect competitors. | John Smith | 2024-04-03
#SP003 | Product Development | Create MVP Wireframes | Design user interface and navigation flow for minimum viable product. | Emily Johnson
#SP004 | Product Development | Prototype Development | Develop interactive prototype for usability testing. | Alex Brown
#SP005 | Team & Resources | Recruit Core Team Members | Hire essential roles including developer, designer, and product manager.
#SP006
#SP007 | Financing & Legal | Prepare Pitch Deck for Investors | Catherine Lee