## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Priority
1 | Define Project Scope | John Doe | 2023-10-01 | 2023-10-05 | Completed | High
2 | Conduct Market Research | Jane Smith | 2023-10-06 | 2023-10-15 | In Progress | High
3 | Develop Business Plan | Mike Johnson | 2023-10-16 | 2023-10-30 | Not Started | High
4 | Create MVP Prototype | Sarah Lee | 2023-10-31 | 2023-11-15 | Not Started | Medium
5 | Secure Initial Funding | David Brown | 2023-11-01 | 2023-11-30 | Not Started | Critical
6 | Hire Core Team | Lisa Garcia | 2023-11-10 | 2023-11-25 | Not Started | Medium
7 | Launch Pilot Program | Tom Wilson | 2023-12-01 | 2023-12-15 | Not Started | High
Total Tasks: | [5 empty] | 7