## Worksheet
Task ID | Task Name | Owner | Status | Start Date | End Date | Progress (%)
T001 | Market Research | Jane Doe | Not Started | 2023-10-01 | 2023-10-15 | 0
T002 | Business Plan Draft | John Smith | In Progress | 2023-10-16 | 2023-11-05 | 65
T003 | Funding Proposal Prep | Alice Brown | In Progress | 2023-10-20 | 2023-11-15 | 40
T004 | Prototype Development | Mike Wilson | In Progress | 2023-11-01 | 2023-12-31 | 75
T005 | Team Hiring Plan | Sarah Lee | Not Started | 2023-11-10 | 2023-11-30 | 0
T006 | Legal & IP Registration | David Chen | In Progress | 2023-11-05 | 2023-12-20 | 50