## Worksheet
Startup Planning - Weekly Project Tracker
Week of | Project Name | Owner | Status | Progress (%) | Key Milestones/Activities | Risks & Issues
2023-10-02 | Market Research Phase 1 | Alice Johnson | In Progress | 65% | - Conducted 20 customer interviews - Completed competitor analysis - Drafted market segmentation report | Delayed response from key industry experts
| User Persona Development | Robert Lee | In Progress | 40% | - Created 3 initial persona drafts - Scheduled feedback session with marketing team - Researching behavioral patterns | Potential mismatch in target audience assumptions
| Initial Product Roadmap | Sarah Kim | Completed | 100% | - Defined MVP features - Set 3-month roadmap timeline - Presented to executive team for approval | No significant issues reported
2023-10-09 | Technical Feasibility Study | James Wilson | In Progress | 55% | - Assessed API integration challenges - Evaluated cloud infrastructure options - Drafted technical architecture diagram | Uncertainty around third-party data licensing
| Initial UI/UX Wireframes | Maria Gonzalez | In Progress | 30% | - Created basic wireframe layouts - Started user flow mapping - Scheduled design review meeting | Need more input from product manager on feature prioritization
2023-10-16 | Seed Funding Pitch Deck | Lisa Chen | Completed | 100% | - Finalized 15-slide pitch deck - Incorporated feedback from advisors - Practiced delivery presentation | No significant issues reported
| Legal Entity Formation | David Park | In Progress | 70% - Filed Articles of Incorporation - Registered trademarks - Set up basic business banking account
2023-10-23 | Core Team Onboarding | Emma Thompson | In Progress | 50% - Completed 2 technical hires - Drafted onboarding checklist - Scheduled training sessions
| First MVP Sprint Planning | Chris Brown | In Progress | 35% - Identified 8 core features - Estimated development timelines - Created sprint backlog
| Early Adopter Outreach | Julia Martin | Delayed | 10% - Reached out to 5 potential beta testers - Waiting for responses to initial invitations - Drafting onboarding guide
Total Projects: 10 ¦ Completed This Week: 3 ¦ In Progress: 6 ¦ Delayed: 1
Weekly Project Tracker - Startup Planning Template ¦ Last Updated: October 25, 2023