## Worksheet
Startup Planning - Annual Schedule Planner
Quarter | Month | Key Objective | Milestone/Activity | Responsible Team | Status
Q1 (Jan - Mar) | January | Founding & Validation | Finalize business idea, validate market need, draft MVP concept | CEO & Product Team | Pending
| February | Team Formation & Funding Prep | Hire core team members; prepare pitch deck and investor materials | Founders & HR Team | Pending
| March | Funding Round Kickoff | Begin outreach to angel investors; conduct first pitch meetings | CEO & CFO | Pending
Q2 (Apr - Jun) | April | Funding Success & Product Build | Secure seed funding; begin MVP development with agile sprints | CFO & Engineering Team | Pending
| May | Early User Testing | Recruit beta users; conduct usability testing sessions with feedback collection | Product & UX Team | Pending
| Q3 (Jul - Sep) | June | Product Refinement & Branding | Incorporate feedback, refine product features; design branding assets | Product & Marketing Team | Pending
Q4 (Oct - Dec) |  | July | Launch Preparation & PR Campaign | Finalize product release plan; launch pre-launch marketing campaign | Marketing & Sales Team | Pending
|  | August | National Launch Event & User Onboarding | Host virtual launch event; onboard initial users and collect first data metrics | CEO & Operations Team | Pending
| September | Performance Review & 2025 Planning | Analyze launch results, refine strategy, draft 2025 roadmap with goals and KPIs | Executive Team & Strategy Lead | Pending
October | Scaling Phase Begins | Expand user acquisition; hire additional customer support and engineering staff | Hiring & Marketing Team | Pending
November | Partnership Development | Negotiate and sign first key partnerships with complementary platforms or distributors | Biz Dev & Legal Team | Pending
December | Year-End Review & Retrospective | Conduct year-end performance review; celebrate achievements and reflect on lessons learned | All Teams | Pending