## Worksheet
Startup Planning - Schedule Planner
Phase | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
Pre-Planning | Market Research & Validation | Alice Johnson | 2024-01-15 | 2024-01-31 | In Progress | $5,000
Pre-Planning | Define MVP Features | Michael Chen | 2024-02-01 | 2024-02-15 | Pending | $3,500
Product Development | UI/UX Design Phase 1 | Sophia Martinez | 2024-02-16 | 2024-03-15 | Pending | $8,750
Product Development | Frontend Development Sprint 1 | James Wilson | 2024-03-16 | 2024-04-15 | Pending | $15,000
Product Development | Backend Development Sprint 1 | Lisa Brown | 2024-03-16 | 2024-04-15 | Pending | $18,500
Testing & QA | User Acceptance Testing (UAT) | Robert Taylor | 2024-04-16 | 2024-05-15 | Pending | $6,800
Launch Preparation | Marketing Campaign Setup | Emily Davis | 2024-05-16 | 2024-06-15 | Pending | $12,000
Launch Preparation | Go-Live Deployment & Monitoring | David Lee | 2024-06-16 | 2024-06-30 | Pending | $7,500
Total Project Budget:$87,050
Current Status:Pre-Planning Phase in Progress
Last Updated: April 5, 2024