## Worksheet
Startup Planning - Schedule Planner (Client View)
Phase | Task | Owner | Start Date | End Date | Status | Budget Allocation ($) | Milestones Achieved (%)
Phase 1: Ideation & Market Validation
1.1 | Market Research and Competitor Analysis | Jane Smith (Product Lead) | 2025-04-05 | 2025-04-19 | In Progress | $8,500 | 65%
1.2 | Define Target Audience Persona | Mike Johnson (Marketing) | 2025-04-10 | 2025-04-23 | Pending | $3,750 | 18%
Phase 2: Business & Product Planning
2.1 | Create MVP Scope and Features List | David Lee (CTO) | 2025-04-15 | 2025-04-30 | Pending | $12,000 | 8%
2.2 | Develop Business Model Canvas & Revenue Streams | Lisa Chen (CEO) | 2025-04-18 | 2025-05-03 | Pending | $6,250 | 12%
Phase 3: Product Development & Testing
3.1 | Design UI/UX Wireframes | Sarah Kim (Designer) | 2025-04-25 | 2025-05-10 | Pending | $7,800 | 3%
3.2 | Build MVP Prototype (Frontend & Backend) | Tom Rodriguez (Fullstack Dev) | 2025-05-15 | 2025-06-30 | Pending | $48,000 | 1%
Phase 4: Launch & Post-Launch Evaluation
4.1 | Conduct Beta Testing with 50 Users | Amy Patel (QA Lead) | 2025-07-01 | 2025-07-31 | Pending | $6,500 | 1%
4.2 | Official Product Launch & Marketing Campaign | Lisa Chen (CEO) | 2025-08-01 | 2025-08-31 | Pending | $35,000 | 1%
Total Project Budget: | [5 empty] | $128,800 | Overall Progress: 25%