## Worksheet
Startup Planning - Schedule Planner Dashboard
Task ID | Task Description | Owner | Start Date | End Date | Status
T001 | Define Core Product Vision & MVP Features | CEO - Jane Doe | 2023-10-05 | 2023-10-15 | In Progress
T002 | Conduct Market Research & Competitor Analysis | Marketing Lead - John Smith | 2023-10-06 | 2023-10-18 | In Progress
T003 | Build Prototype & Initial UI/UX Design | CTO - Alex Johnson | 2023-10-10 | 2023-10-25 | In Progress
T004 | Secure Seed Funding Pitch Deck & Investor Outreach | CEO - Jane Doe | 2023-10-12 | 2023-10-31 | Pending
T005 | Finalize Legal Structure & Incorporation Papers | Legal Advisor - Maria Garcia | 2023-10-15 | 2023-10-28 | In Progress
T006 | Develop MVP Development Roadmap (Engineering) | CTO - Alex Johnson | 2023-10-18 | 2023-11-05 | Pending
T007 | Recruit Core Founding Team Members | HR Manager - David Lee | 2023-10-20 | 2023-11-15 | Pending
T008 | Setup Company Infrastructure & Tools (Git, Slack, CRM) | CTO - Alex Johnson | 2023-10-25 | 2023-11-03 | Pending
T009 | Conduct First User Testing with Beta Group | Product Manager - Sarah Kim | 2023-11-05 | 2023-11-17 | Pending
T010 | Launch MVP to Early Adopters (Public Beta) | CEO - Jane Doe | 2023-11-20 | 2023-12-05 | Pending
Dashboard Summary:Total Tasks: 10 ¦ In Progress: 4 ¦ Pending: 6 ¦ Completed: 0