## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Priority
T001 | Market Research & Analysis | 2025-04-01 | 2025-04-15 | In Progress | Jane Doe | High
T002 | Business Plan Drafting | 2025-04-16 | 2025-04-30 | Pending | John Smith | High
T003 | Funding Proposal Development | 2025-05-01 | 2025-05-15 | Pending | Sarah Lee | High
T004 | Prototype Development (MVP) | 2025-05-16 | 2025-06-15 | Pending | Mike Chen | High
T005 | User Testing & Feedback Collection | 2025-06-16 | 2025-07-15 | Pending | Lisa Wang | Medium
T006 | Finalize Product Features & Roadmap | 2025-07-16 | 2025-07-31 | Pending | Daniel Park | Medium
T007 | Launch Preparation (Marketing & PR) | 2025-08-01 | 2025-08-31PendingAmanda Brown | High
This schedule planner is designed for startup planning purposes. Status and dates are subject to change based on project progress.