## Worksheet
Startup Planning - Schedule Planner (Detailed)
Task ID | Task Description | Owner | Start Date | End Date | Status | Priority Level
01-001 | Market Research & Competitor Analysis | Marketing Team | 2024-04-15 | 2024-04-30 | In Progress | High
01-002 | Define Core Value Proposition | Product Team | 2024-04-18 | 2024-05-15 | Not Started | High
02-001 | Wireframe & UX Design (Web Platform) | Design Team | 2024-05-16 | 2024-06-15 | Not Started | High
02-002 | Backend API Development (Node.js) | Engineering Team | 2024-05-16 | 2024-07-31 | Not Started | High
03-001 | Alpha Testing with Internal Team | QA Team | 2024-08-01 | 2024-08-31 | Not Started | Medium
04-001 | Prepare Go-to-Market Strategy | Marketing & Sales Team | 2024-07-15 | 2024-08-31 | Not Started | High
05-001 | Soft Launch to Beta Users (100 people) | Product & Support Team | 2024-09-15 | 2024-11-30 | Not Started | Medium
06-001 | Full Public Release & Marketing Campaign | Entire Team | 2024-12-01 | 2024-12-31 | Not Started | High
Total Tasks: |  |  | 8
Legend:
High- Critical tasks requiring immediate attention.
Medium- Important but less urgent tasks.
Low- Optional or supporting activities.