## Worksheet
STARTUP PLANNING - SCHEDULE PLANNER (EXTENDED)
Phase | Task | Owner | Start Date | End Date | Status | Priority (High) | Priority (Medium) | Priority (Low)
PHASE 1: IDEATION & RESEARCH
Research | Market Need Validation | Product Lead | 2024-05-01 | 2024-05-15 | In Progress
Research | Competitor Analysis | Market Analyst | 2024-05-10 | 2024-05-31 | Pending
PHASE 2: BUSINESS DESIGN
Design | Business Model Canvas | CEO | 2024-06-01 | 2024-06-15 | Pending
PHASE 3: PROTOTYPE DEVELOPMENT
Development | MVP Wireframe Design | UX Designer | 2024-06-15 | 2024-07-15 | Pending
PHASE 4: FUNDING & PLANNING
Planning | Pitch Deck Creation | CEO/Marketing | 2024-07-15 | 2024-08-15 | Pending
PHASE 5: LAUNCH PREPARATION
Preparation | Go-to-Market Strategy | Marketing Lead | 2024-08-15 | 2024-09-15 | Pending
PHASE 6: PUBLIC LAUNCH
Launch | Product Release & Marketing Push | CEO / Team Lead | 2024-09-15 | 2024-10-31 | Pending
Total Tasks: |  |  |  | 9 |  | 3 | 3 | 3
PROJECT TIMELINE: May 2024 – October 2024