## Worksheet
Startup Planning - Schedule Planner (Financial View)
Track key milestones, budget allocations, and financial projections in one comprehensive table.
Phase / Milestone | Timeline |  |  | Budget Allocation (USD) |  |  | Status
| Start Date | End Date | Duration (weeks) | Planned | Actual | Variance (%)
Ideation & Market Research | 2024-01-05 | 2024-01-31 | 5 | $8,500 | $7,950 | -6.47% | On Track
Product Prototyping & MVP Build | 2024-02-01 | 2024-05-15 | 16 | $85,300 | $89,750 | +5.22% | Slight Delay
Funding Round Prep & Investor Pitching | 2024-04-01 | 2024-06-30 | 13 | $15,500 | $17,895 | +15.45% | Over Budget
Marketing Campaign & Community Building | 2024-05-15 | 2024-08-31 | 15 | $67,800 | $64,375 | -5.05% | On Track
Product Launch & Early Customer Acquisition | 2024-09-01 | 2024-11-30 | 13 | $75,450 | $78,695 | +4.29% | On Track (Minor Over)
Total |  |  | 52 weeks | $252,550 | $268,665 | +6.38% | Overall: Slight Budget Overrun
Last updated on2024-10-15. Data reflects current financial and timeline status for startup planning.