## Worksheet
Startup Planning - Schedule Planner (Freelancer Style)
Task | Description | Start Date | End Date | Status | Assigned To
Define Business Idea | Craft a clear and unique value proposition for the startup. | 2024-04-01 | 2024-04-05 | Completed | Jane Smith
Market Research & Analysis | Conduct surveys and analyze target market trends. | 2024-04-06 | 2024-04-15 | Pending | Mike Chen
Create Business Model Canvas | Develop a visual framework for the business strategy. | 2024-04-16 | 2024-04-18 | Pending | Lisa Kim
Develop MVP Prototype | Build a minimum viable product for user testing. | 2024-04-19 | 2024-05-10 | Pending | David Wilson
User Testing & Feedback Collection | Run beta tests with 20 users and gather insights. | 2024-05-11 | 2024-05-18 | Pending | Jane Smith
Finalize Product Roadmap | Update product plan based on feedback and priorities. | 2024-05-19 | 2024-05-23 | Pending | Lisa Kim
Secure Initial Funding | Prepare pitch deck and reach out to investors. | 2024-05-24 | 2024-06-15 | Pending | Mike Chen
Form Core Team | Hire 3 key team members (Dev, Designer, Marketing). | 2024-06-16 | 2024-07-05 | Pending | David Wilson
Launch Public Beta | Release product version 1.0 to early adopters. | 2024-07-06 | 2024-07-31 | Pending | All Team
This schedule planner is designed for freelancers and startup founders to track milestones, deadlines, and responsibilities efficiently.