## Worksheet
Task ID | Task Name | Category | Owner | Start Date | Due Date | Status | Priority
Phase 1: Foundation (July 1 - July 15)
FP-001 | Define Business Vision & Mission | Strategy | Sarah Johnson | 2024-07-01 | 2024-07-05 | Completed | High
FP-002 | Conduct Market Research & Analysis | Research | Liam Chen | 2024-07-03 | 2024-07-15 | In Progress | High
Phase 2: Planning (July 16 - August 5)
PL-001 | Develop Business Model Canvas | Strategy | Sarah Johnson | 2024-07-16 | 2024-07-25 | In Progress | High
PL-002 | Create 12-Month Financial Projections | Finance | Aisha Patel | 2024-07-18 | 2024-08-05 | Pending | Medium
Phase 3: Execution (August 6 - September 15)
EX-001 | Finalize MVP Design & Features | Product | Ryan Miller | 2024-08-152024-09-01 | Pending | High
EX-002 | Recruit Core Development Team | Hiring | Lisa Wong | 2024-08-152024-09-15 | Pending | Medium
Phase 4: Review & Launch Preparation (September 16 - September 30)
RP-001 | Conduct Final Product Review | Product | Ryan Miller | 2024-09-162024-09-25 | Pending | High
RP-002 | Prepare Launch Marketing Campaign | Marketing | Elena Rodriguez | 2024-09-182024-09-30 | Pending | Medium