## Worksheet
Startup Planning - Schedule Planner (Manager View)
Task ID | Task Name | Owner | Start Date | End Date | Status | Prioritization Level
Phase 1: Ideation & Research (Jan 5 – Jan 20)
TSK-001 | Market Analysis | Sarah Chen | 2024-01-05 | 2024-01-12 | In Progress | High
TSK-002 | User Persona Development | James Rivera | 2024-01-08 | 2024-01-15 | Pending Review | Medium
Phase 2: Product Design & Planning (Jan 16 – Feb 10)
TSK-003 | UI/UX Wireframing | Linda Park | 2024-01-16 | 2024-01-31 | To Do | High
Phase 3: Development & Testing (Feb 5 – Mar 20)
TSK-010 | MVP Launch Ready | Tech Team Lead | 2024-03-18 | 2024-03-20 | Critical Milestone | High
Phase 4: Go-to-Market (Mar 15 – Apr 30)
TSK-012 | Marketing Campaign Launch | Marketer Alex | 2024-03-15 | 2024-04-15 | In Progress | Medium
Phase 5: Post-Launch Review (May 1 – May 30)
TSK-015 | Post-MVP Feedback Analysis | Product Team | 2024-05-01 | 2024-05-30 | To Do | Low
Legend:
• High Priority Tasks are highlighted in red background
• Medium Priority Tasks are highlighted in yellow background
• Low Priority Tasks are highlighted in green background
• Milestone tasks appear with bold text and orange color