## Worksheet
Startup Planning - Schedule Planner
Multi-Page Template for Comprehensive Project Management
Phase 1: Vision & Foundation (Weeks 0–4)
Task | Owner | Start Date | End Date | Status
Define mission, vision, and core values | CEO & Founders | 2023-10-02 | 2023-10-15 | Pending
Create business concept document (BCD) | Biz Dev Lead | 2023-10-09 | 2023-10-18 | In Progress
Conduct initial market research & competitor analysis | Data Analyst Team | 2023-10-16 | 2023-10-30 | Pending
Finalize target customer personas (TCPs) | Marketing Lead | 2023-10-25 | 2023-11-04 | Pending
Draft initial pitch deck for investors | CFO & CEO | 2023-10-30 | 2023-11-07 | Pending
Key Milestones (Phase 1)
Completion of Vision & Mission Statement – Week 4
First Draft of Business Concept Document – Week 3
Initial Market Research Report Finalized – Week 5
Progress Overview:
35%
Phase 2: Product Development (Weeks 5–16)
Task | Owner | Start Date | End Date | Status
Create product wireframes & UI/UX mockups | Design Lead | 2023-11-06 | 2023-11-27 | Pending
Develop MVP (Minimum Viable Product) | Tech Team (CTO) | 2023-11-30 | 2024-01-15 | Pending
Conduct internal beta testing (v1.0) | QA & Dev Team | 2024-01-16 | 2024-01-30 | Pending
Implement feedback & refine features (v1.1) | Tech Team & Product Manager | 2024-02-05 | 2024-02-19 | Pending
Prepare for soft launch (internal + pilot users) | Marketing & DevOps | 2024-03-15 | 2024-03-31 | Pending
Key Milestones (Phase 2)
MVP Development Complete – Week 14
Internal Beta Test Launched – Week 15
Soft Launch with Pilot Users – Week 20
Progress Overview:
15%
Phase 3: Market Launch & Growth (Weeks 17–26)
Task | Owner | Start Date | End Date | Status
Finalize go-to-market strategy & pricing model | CFO & Marketing Lead | 2024-03-15 | 2024-03-31 | Pending
Launch public beta (open to early adopters) | Tech & Marketing Team | 2024-04-01 | 2024-05-15 | Pending
Run first marketing campaign (digital ads, email, content) | Marketing Lead & Content Team | 2024-04-15 | 2024-06-30 | Pending
Analyze user feedback & iterate on product (v1.5) | Product & Dev Team | 2024-05-16 | 2024-06-30 | Pending
Campaign for Series A funding (pitch deck refinement) | CEO & CFO | 2024-05-15 | 2024-07-31 | Pending
Key Milestones (Phase 3)
Public Beta Launch – Week 18
First Marketing Campaign Live – Week 20
Series A Fundraising Target Reached – Week 26
Progress Overview:
5%
Phase 4: Finance & Operations (Ongoing)
Financial Item | Target Amount ($) | Current Balance ($) | Status
Seed Funding Raised (Target) | 500,000 | 387,421 | In Progress
Monthly Operating Budget (Avg.) | 65,231 | 62,199 | Funded & On Track
R&D Expenses (Q3) | 80,000 | 74,532 | In Progress
Sales & Marketing Budget (Q3) | 125,000 | 98,641 | In Progress
Team Headcount (Full-Time) | 12 | 9 | Pending Hire(s)
Operational Goals (Next 6 Months)
Onboard all core team members by end of Q3
Set up HR, payroll, and legal compliance systems
Implement CRM and project tracking tools (e.g., Asana, Salesforce)
Funding Progress:
77%
*Note: Regular financial reviews are scheduled for the first Friday of each month.
Phase 5: Review & Strategic Adjustment
This phase is designed for periodic evaluation and iteration based on performance metrics, user feedback, and market changes.
Review Cycle | Focus Area | Key Metrics to Track | Action Plan / Adjustments
Quarterly (Q4) | Product Performance | User retention rate, feature usage, bug reports | Refine UI based on analytics; prioritize high-impact features
Monthly (Every 1st Friday) | Financial Health | Cash runway, burn rate, revenue growth | Adjust budget allocations if needed; forecast next quarter expenses
Semi-Annual (June & December) | Market Positioning | User acquisition cost (CAC), lifetime value (LTV), competitor shifts | Reassess positioning strategy and messaging; explore new channels
Next Steps & Planning Horizon
Prepare for Series A funding round by Q4 (target $2M)
Expand team with sales, customer success, and product managers
Pilot international market expansion (UK & Canada) in early 2025
Overall Project Status:On Track – Phases 1–2 in progress, Phase 3 starting soon.
Total Timeline Progress:~20% completed (out of estimated 52 weeks).