## Worksheet
Startup Planning - Schedule Planner (Office Use)
Task | Owner | Start Date | End Date | Status | % Complete | Notes/Comments
Phase 1: Ideation & Market Research (Weeks 1-4)
Define core business idea and value proposition | CEO | 2023-10-02 | 2023-10-15 | In Progress | 75% | N/A
Conduct market research and customer interviews | Marketing Lead | 2023-10-04 | 2023-10-18 | To Do | 0% | Target 5 customer interviews per week.
Phase 2: Business Development (Weeks 5-8)
Develop business model canvas | CEO & CFO | 2023-10-19 | 2023-11-05 | To Do | 0% | Draft and present to advisory board.
Create financial projections (P&L, Cash Flow, Balance Sheet) | CFO | 2023-10-23 | 2023-11-15 | To Do | 0% | Budget for first 6 months.
Phase 3: Product Development (Weeks 9-16)
Design MVP wireframes and user flows | Product Manager | 2023-11-06 | 2023-11-25 | To Do | 0% | Prioritize core features only.
Develop initial prototype (MVP) | Lead Developer | 2023-11-27 | 2024-01-15 | To Do | 0% | Sprint-based development with bi-weekly reviews.
Phase 4: Launch Preparation (Weeks 17-20)
Finalize product testing and bug fixes | QA Lead | 2024-01-16 | 2024-01-30 | To Do | 0% | User acceptance testing (UAT) scheduled.
Create go-to-market strategy and marketing materials | Marketing Lead | 2024-01-23 | 2024-02-15 | To Do | 0% | Email campaign, landing page, social media plan.
Phase 5: Go-Live & Post-Launch (Weeks 21-24)
Launch product publicly | CEO & Team | 2024-02-16 | 2024-02-17 | To Do | 0% | Landing page live, initial user onboarding.
Monitor performance metrics and collect user feedback | Data Analyst & Support Team | 2024-02-18 | 2024-03-17 | To Do | 0% | Daily monitoring, weekly review meetings.
Project Timeline Summary: Total Duration - 24 Weeks (6 Months)