## Worksheet
Startup Planning - Schedule Planner
Phase | Task Description | Start Date | End Date | Responsible Person | Status
Phase 1: Ideation & Concept Validation
1.1 | Market Research and Opportunity Identification | 2025-04-01 | 2025-04-15 | Jane Doe | In Progress
1.2 | Customer Interviews & Feedback Collection | 2025-04-16 | 2025-04-30 | John Smith | Pending
Phase 2: Product Development
2.1 | Define Core Features & MVP Scope | 2025-05-01 | 2025-05-10 | Maria Lopez | Pending
2.2 | Design UI/UX Prototypes | 2025-05-11 | 2025-05-31 | Alex Chen | Pending
Phase 3: Team & Infrastructure Setup
3.1 | Hire Core Development Team | 2025-06-01 | 2025-06-15 | Sarah Williams | Pending
3.2 | Set Up Cloud Infrastructure & DevOps Pipeline | 2025-06-16 | 2025-06-30 | David Brown | Pending
Phase 4: Launch Preparation & Marketing
4.1 | Develop Pre-Launch Marketing Campaign | 2025-07-01 | 2025-07-15 | Lisa Garcia | Pending
Phase 5: Official Launch & Post-Launch Review
5.1 | Final Testing & QA Release | 2025-07-16 | 2025-07-31 | Maria Lopez | Pending
5.2 | Public Launch Event & Go Live | 2025-08-01 | 2025-08-01 | All Team Members | Pending
Total Duration: 4 Months (April 1st - August 1st)