## Worksheet
Startup Planning - Schedule Planner
Week | Date Range | Key Milestone | Task Description | Responsible Person | Status
Week 1 | Jan 1 - Jan 7 | Market Research Complete | Conduct competitor analysis and customer surveys. | Jane Doe | Pending
Week 2 | Jan 8 - Jan 14 | Business Model Finalized | Define value proposition and revenue streams. | John Smith | In Progress
Week 3 | Jan 15 - Jan 21 | MVP Design Phase Start | Create wireframes and user flow diagrams. | Alex Lee | Pending
Week 4 | Jan 22 - Jan 28 | Team Onboarding Complete | Finalize team roles and conduct onboarding sessions. | Sarah Kim | Pending
Week 5 | Jan 29 - Feb 4 | MVP Development Begins | Start coding core features of the prototype. | Daniel Brown | Pending
Week 6 | Feb 5 - Feb 11 | User Testing Prep Complete | Recruit beta users and prepare test scenarios. | Lisa Chen | Pending
Week 7 | Feb 12 - Feb 18 | MVP Beta Launch | Release MVP to a small group of beta users. | Alex Lee | Pending
Week 8 | Feb 19 - Feb 25 | Feedback Integration Phase Start | Analyze feedback and prioritize improvements. | Jane Doe | Pending
Project Summary & Next Steps
Current Phase:Planning & Research |  |  | Target Completion Date:Feb 25, 2024