## Worksheet
Startup Planning - Schedule Planner (Planning View)
Task ID | Task Name | Category | Start Date | End Date | Status | Owner(s)
Phase 1: Concept & Validation (Weeks 1-4)
TP001 | Market Research & Problem Discovery | Research | 2025-04-07 | 2025-04-18 | In Progress | Alice Chen, Jordan Lee
MS101 | MVP Concept Validation (Customer Interviews) | Milestone: Week 3 |  | Completed
Phase 2: Product Development (Weeks 5-10)
TP002 | Wireframing & UX Design | Design |  |  |  | Samira Patel, Tyler Wong
TP003 | Development Sprint 1 (Core Features) | Sprint 1: Week 7 |  | Due: 2025-05-16
Phase 3: Testing & Launch Preparation (Weeks 11-14)
TP004 | User Acceptance Testing (UAT) | Testing Phase |  | Scheduled: 2025-06-13 to 2025-06-19
MS104 | Final Product Sign-off & Go-Live Readiness | Milestone: Week 14 |  | Due: 2025-06-30
Phase 4: Post-Launch Review & Iteration (Weeks 15+)
TP005 | Launch Day Execution & Monitoring | Go-Live |  | Scheduled: 2025-07-01
Note:This is a planning view template. Adjust dates, owners, and statuses as needed during execution.