## Worksheet
Startup Planning - Schedule Planner
Professional Template for Project Milestones and Task Management
Task ID | Task Description | Responsible Team Member | Start Date | End Date | Status | Milestone Type
#STP-001 | Market Research and Feasibility Analysis | Product Team Lead | 2024-01-15 | 2024-02-15 | In Progress | Milestone 1: Research Phase
#STP-002 | Business Model Development | CEO & Strategy Director | 2024-01-25 | 2024-03-15 | Pending | Milestone 2: Planning Phase
#STP-003 | Prototype Design and Wireframing | Design & UX Team | 2024-02-15 | 2024-03-31 | In Progress | Milestone 3: Design Phase
#STP-004 | Technical Architecture Planning | CTO & Engineering Lead | 2024-03-15 | 2024-04-15 | Pending | Milestone 4: Infrastructure Setup
#STP-005 | Initial Funding Pitch Preparation | CEO & Finance Director | 2024-03-31 | 2024-05-15 | Pending | Milestone 5: Funding Readiness
#STP-006 | Early Beta Testing with Pilot Users | Product & QA Team | 2024-05-15 | 2024-07-31 | Pending | Milestone 6: Testing Phase
#STP-007 | Launch Preparation & Marketing Campaigns | Marketing & Operations Team | 2024-06-15 | 2024-08-31 | Pending | Milestone 7: Go-to-Market Phase
Notes:
- This template is designed for professional startup planning and scheduling.
- Status indicators reflect current progress (Pending, In Progress, Completed).