## Worksheet
Startup Planning - Schedule Planner (Report Version)
Comprehensive Project Timeline & Milestone Tracker
Phase | Activity | Owner | Start Date | End Date | Status | Budget Allocated ($)
Phase 1: Ideation & Validation
Research | Market Analysis and Competitor Review | Jane Doe - Product Lead | 2024-01-05 | 2024-01-19 | In Progress | 8,500
Research | User Persona Development | Mark Lee - UX Designer | 2024-01-12 | 2024-01-31 | Pending | 5,750
Phase 2: Product Development
Design | UI/UX Wireframing & Prototyping | Mark Lee - UX Designer | 2024-02-01 | 2024-03-15 | Pending | 18,900
Development | Core Feature Implementation (MVP) | Alice Chen - CTO | 2024-03-16 | 2024-05-31 | Pending | 85,000
Phase 3: Testing & Launch
QA | Functional & Usability Testing | Robert Kim - QA Manager | 2024-06-01 | 2024-06-30 | Pending | 15,500
Total Project Budget: | [5 empty] | 133,650