## Worksheet
Task | Start Date | End Date | Owner | Status
Market Research & Analysis | 2023-10-01 | 2023-10-15 | Jane Smith | In Progress
Business Plan Development | 2023-10-16 | 2023-10-31 | John Doe | Pending
Funding Pitch Preparation | 2023-11-01 | 2023-11-10 | Alice Johnson | Pending
Legal Entity Registration | 2023-11-11 | 2023-11-20 | Robert Brown | Pending
Website Development | 2023-11-21 | 2023-12-05 | Lisa Wong | Pending
Product Prototype Design | 2023-11-21 | 2023-12-15 | Daniel Kim | Pending
Initial Marketing Campaign Setup | 2023-12-06 | 2023-12-15 | Sophia Martinez | Pending
Team Onboarding & Training | 2023-12-16 | 2023-12-31 | Maria Garcia | Pending