## Worksheet
Startup Planning - Schedule Planner (Summary View)
Phase | Key Milestone | Start Date | End Date | Status | Owner | Description
Phase 1: Ideation & Research | Market Research Completion | 2024-04-01 | 2024-05-15 | In Progress | Jane Doe | Analyze target market, competitors, and customer needs.
| Business Model Finalization | 2024-05-16 | 2024-06-15 | Pending | John Smith | Define revenue streams, pricing, and value proposition.
| Idea Validation Workshop | 2024-06-16 | 2024-07-31 | Pending | Alice Brown | Present findings and validate core business idea with stakeholders.
Phase 2: Planning & Setup | Legal Entity Registration | 2024-08-01 | 2024-09-15 | Pending | Robert Lee | Incorporate company and register trademarks.
| Team Formation & Hiring | 2024-09-16 | 2024-11-30 | Pending | Sarah Wilson | Hire core team members (Tech, Marketing, Operations).
| Office & Infrastructure Setup | 2024-10-01 | 2024-11-30 | Pending | Mark Taylor | Secure workspace, IT systems, and tools.
| Funding Strategy & Pitch Deck Finalized | 2024-11-01 | 2024-12-31 | Pending | Lisa Garcia | Develop investor pitch and funding roadmap.
Phase 3: Development & Launch | Product Prototype Complete | 2025-01-01 | 2025-04-30 | Pending | David Kim | Build and test MVP with initial users.
| User Testing & Feedback Loop | 2025-05-01 | 2025-06-30 | Pending | Nina Patel | Gather and analyze feedback for product improvements.
| Official Launch (Beta Release) | 2025-07-01 | 2025-07-31 | Pending | All Team Members | Launch beta version to early adopters and collect metrics.
Total Timeline: |  |  |  | 2024-04-01 to 2025-12-31
This schedule is a living document. Updated monthly by the Project Management Office.