## Worksheet
Startup Planning - Schedule Planner
Template Version: v2.3 ¦ Purpose: Startup Planning ¦ Type: Schedule Planner
Phase | Task Name | Owner | Start Date | End Date | Status | Milestones
Phase 1: Ideation
| Market Research & Validation | John Doe | 2024-04-01 | 2024-04-15 | In Progress | Competitor Analysis Complete, Customer Surveys Sent Out
| Define Core Value Proposition | Jane Smith | 2024-04-16 | 2024-04-30 | Pending
Phase 2: Product Development
| Wireframing & UX Design | Mike Johnson | 2024-05-01 | 2024-05-15 | Pending
| Prototype Development (MVP) | Amy Lee | 2024-05-16 | 2024-06-30 | In Progress | MVP Prototype Completed, First User Test Run Scheduled
| Backend Development Setup | Carlos Martinez | 2024-06-01 | 2024-07-15 | Pending
| Alpha Testing & Feedback Loop | Sarah Wilson | 2024-07-16 | 2024-08-31 | Pending
Phase 3: Go-to-Market
| Brand Identity & Logo Design | Emily Brown | 2024-09-01 | 2024-09-15 | Pending
| Marketing Campaign Planning (Digital & Social) | Tony Reed | 2024-09-16 | 2024-10-31 | Pending
| Landing Page & Pre-Signup Funnel Setup | Lisa Chen | 2024-11-01 | 2024-11-30 | Pending
Phase 4: Launch & Scale
| Soft Launch (Beta Release) | David Kim | 2024-12-01 | 2025-01-31 | Pending
| Full Public Launch & PR Campaign | Rachel Green | 2025-02-01 | 2025-03-31 | Pending
* This schedule is subject to change based on feedback, market conditions, and resource availability.