## Worksheet
Startup Planning - Task Manager (Analysis View)
Task ID | Task Description | Owner | Due Date | Prioritization Level | Status | Budget Estimate ($)
T001 | Market Research and Competitor Analysis | Jane Smith | 2024-04-30 | High | In Progress | 5,000.00
T015 | Define MVP Features and User Journey Map | Mike Chen | 2024-05-15 | High | Pending | 3,800.00
T221 | Develop Initial Wireframes and UI Mockups | Sarah Johnson | 2024-05-10 | Medium | In Progress | 8,500.00
T342 | Prepare Pitch Deck for Investor Meeting | Daniel Lee | 2024-06-15 | Low | Pending | 2,700.00
T412 | Conduct Initial Customer Interviews (15 participants) | Lisa Wang | 2024-05-31 | Medium | Pending | 4,200.00
T567 | Secure First Round of Seed Funding (Target: $500K) | Robert Garcia | 2024-06-30 | High | Pending | 15,000.00
T789 | Build Core Team (Hiring Plan & Job Descriptions) | Amanda Torres | 2024-06-15 | Low | Completed | 6,300.00
Legend:
High Priority– Critical tasks for startup launch.
Medium Priority– Important but not time-sensitive.
Low Priority– Supportive or long-term planning.
Status:Pending = Not started, In Progress = Active, Completed = Finished.