## Worksheet
Startup Planning - Annual Task Manager (Annual)
Quarter | Task Name | Description | Responsible Person | Status | Due Date
Q1 | Market Research & Analysis | Gather insights on target audience, competitors, and industry trends. | Marketing Lead | In Progress | 2024-03-31
Q1 | Business Plan Finalization | Finalize the complete business plan for investor and internal use. | CFO | To Do | 2024-03-15
Q2 | Product Prototype Development | Create functional prototype for customer testing. | Product Manager | In Progress | 2024-06-30
Q2 | Fundraising Preparation | Prepare pitch deck, financial model, and investor outreach plan. | CFO / CEO | In Progress | 2024-06-15
Q3 | User Testing & Feedback Integration | Conduct beta testing and incorporate feedback into product. | Product Team | To Do | 2024-09-30
Q3 | Hiring Key Staff Roles | Recruit core team members for engineering, sales, and marketing. | HR Manager | To Do | 2024-09-15
Q4 | Landing Page & MVP Launch | Deploy website and launch minimum viable product (MVP). | CTO / Marketing Lead | To Do | 2024-12-31
Q4 | Year-End Performance Review | Evaluate progress, adjust strategy, and plan for next year. | CEO | To Do | 2024-12-15