## Startup Planning - Task Manager
Startup Planning - Task Manager (Detailed)
ID | Task Name | Description | Assigned To | Due Date | Status | Priority
STP-001 | Define Business Model | Develop the core business model including revenue streams, customer segments, and value propositions. | Jane Smith | 2024-12-31 | In Progress | High
STP-002 | Market Research & Analysis | Conduct comprehensive research on target market size, competition, and customer needs. | Mike Johnson | 2025-01-15 | Pending | High
STP-003 | Create MVP Prototype | Design and develop a minimum viable product for initial user testing. | Amy Lee | 2025-01-31 | Pending | High
STP-004 | Secure Seed Funding | Prepare pitch deck and approach potential angel investors and VC firms. | Daniel Brown | 2025-03-15 | Pending | Medium
STP-005 | Legal Entity Formation | Register the company, obtain EIN, and set up necessary legal documents. | Lisa Wong | 2024-12-15 | Completed | Low
STP-006 | Build Core Team | Hire key roles: CTO, Head of Marketing, and COO. | James Wilson | 2025-02-14 | Pending | Medium
STP-007 | Develop Brand Identity | Create logo, brand guidelines, and website mockups. | Sophie Martin | 2025-01-31 | In Progress | Medium
STP-008 | Initial User Testing | Run usability tests with 10-15 target users on the MVP. | Amy Lee | 2025-03-31 | Pending | High
STP-009 | Prepare Launch Plan | Create go-to-market strategy, marketing materials, and launch timeline. | Lisa Wong | 2025-04-15 | Pending | Medium
STP-010 | Finalize Funding Round Terms | Negotiate valuation, cap table structure, and investor agreements. | Daniel Brown | 2025-03-31 | Pending | High
Updated on October 5, 2024 ¦ Startup Planning - Task Manager Template (Detailed Version)