## Worksheet
Startup Planning - Task Manager (Extended)
ID | Task Name | Description | Assigned To | Due Date | Status | Priority
001 | Develop Business Model Canvas | Create a comprehensive business model using the BMC framework. | Alice Johnson | 2024-04-30 | In Progress | High
002 | Conduct Market Research | Analyze target market size, trends, and customer needs. | Robert Chen | 2024-05-15 | Pending | High
003 | Build MVP Prototype | Develop a minimum viable product prototype for initial testing. | Lisa Wong | 2024-06-10 | In Progress | High
004 | Secure Seed Funding Pitch Deck | Create investor-ready pitch materials including financials and roadmap. | James Reed | 2024-05-25 | Pending | Medium
005 | Set Up Legal Structure & Incorporation | Register the company and finalize legal documentation. | Sarah Thompson | 2024-04-28 | Completed | High
006 | Design Brand Identity & Logo | Create brand guidelines, color scheme, and logo design. | Emily Rodriguez | 2024-05-18 | In Progress | Medium
007 | Develop Customer Acquisition Strategy | Outline channels, messaging, and KPIs for early user growth. | Derek Kim | 2024-06-30 | Pending | Medium
008 | Build Website & Landing Page | Develop responsive site with core features and clear CTA. | Maria Lopez | 2024-06-15 | Pending | High
009 | Onboard Initial Beta Testers | Recruit and onboard first 50 users for product feedback. | Taylor Brown | 2024-07-12 | Pending | Medium
010 | Finalize Funding Round Terms | Negotiate term sheets and prepare for closing. | Chris Nelson | 2024-07-31 | Pending | High
Generated on April 5, 2024 ¦ Startup Planning Task Manager (Extended Version)