## Startup Planning Task Manager
Startup Planning Task Manager
Track, manage, and organize your startup’s key tasks with this structured template.
Task ID | Task Description | Owner | Due Date | Priority | Status
T001 | Define core value proposition and target market | Alice Johnson | 2024-11-30 | High | In Progress
T002 | Create MVP wireframes and user flow diagrams | Michael Chen | 2024-11-15 | Medium | In Progress
T003 | Secure initial seed funding from angel investors | David Rodriguez | 2024-12-10 | High | On Hold
T004 | Set up company legal structure and domain registration | Sarah Williams | 2024-11-25 | Low | Completed
T005 | Build initial marketing landing page with sign-up form | James Foster | 2024-11-28 | Medium | In Progress
T006 | Conduct first customer interviews for product validation | Linda Park | 2024-11-20 | High | On Hold
T007 | Establish communication channels (Slack, email, etc.) | Robert Kim | 2024-11-18 | Low | Completed
T008 | Develop detailed product roadmap for Q1 2025 | Claudia Mendez | 2024-12-5 | Medium | In Progress
T009 | Finalize pitch deck for investor meetings | Marcus Lee | 2024-11-30 | High | In Progress
T010 | Register for startup accelerators and pitch events | Elena Torres | 2024-12-8 | Low | In Progress