## Worksheet
Startup Planning - Advanced Time Tracker
Date | Project Phase | Task Description | Assigned To | Start Time | End Time | Total Hours | Status
Research & Market Analysis Phase (Week 1-2)
2023-10-05 | Market Research | Conduct competitor analysis for 5 similar startups | Alice Chen | 09:00 AM | 12:30 PM | 3.5 | Completed
2023-10-06 | Market Research | Interview 10 potential users for feedback on pain points | Bryan Lee | 10:30 AM | 2:45 PM | 4.25 | Completed
2023-10-07 | User Persona Development | Create 3 detailed user personas based on research data | Clara Rodriguez | 08:45 AM | 11:30 AM | 2.75
2023-10-08 | Data Compilation & Reporting | Compile research findings into a comprehensive report (draft) | Alice Chen | 1:30 PM | 4:15 PM
Product Development Phase (Week 3-6)
2023-10-12 | Wireframing | Create wireframes for core app screens (homepage, dashboard, profile) | Daniel Kim | 9:15 AM | 1:00 PM
2023-10-13 | Design System Creation | Establish color palette, typography, and UI components library | Jessica Taylor
2023-10-15 | Backend Architecture Planning | Design database schema and API endpoints structure | Marcus Johnson
2023-10-16 | Frontend Development | Implement responsive layout using React components | Sophia Wang
Testing & Validation (Week 7-8)
2023-10-19 | QA Testing | Perform unit and integration testing on all features | Alice Chen, Bryan Lee
2023-10-21 | User Acceptance Testing (UAT) | Run beta test with 5 external users; collect feedback | Clara Rodriguez, Daniel Kim
2023-10-23 | Iterative Improvements | Implement feedback into product; fix critical bugs | Sophia Wang, Marcus Johnson
Total Hours (All Phases): | [5 empty] | 43.25