## Worksheet
Startup Planning - Time Tracker - Analysis View
Project Phase | Task Description | Start Date | End Date | Status | Planned Hours | Actual Hours | % Complete
Research & Discovery | Market Research and Competitive Analysis | 2024-01-15 | 2024-01-31 | In Progress | 48.5 | 36.7 | 75%
Ideation & Concept Development | Create Initial Product Wireframes and User Flow Maps | 2024-01-20 | 2024-01-31 | Completed | 35 | 34.8 | 99%
Prototyping & Testing | User Testing with MVP Prototype (Round 1) | 2024-02-01 | 2024-02-15 | Pending | 56.8 | 0 | 0%
Development Phase 1 | Frontend Implementation (Core Features) | 2024-02-16 | 2024-03-15 | In Progress | 89.5 | 67.3 | 75%
Development Phase 1 | Backend Integration and API Development | 2024-02-16 | 2024-03-31 | In Progress | 98.5 | 76.1 | 77%
Total Time Summary |  |  |  |  | 328.3 | 254.9 | 77%
This report was generated on:. Time Tracker - Analysis View ¦ Startup Planning Template