## Worksheet
Task | Start Date | End Date | Status | Assigned To | Hours Logged
Market Research | 2023-10-01 | 2023-10-15 | In Progress | Jane Smith | 48.5
Product Development Plan | 2023-10-16 | 2023-11-05 | To Do | John Doe | 0
Funding Proposal Draft | 2023-11-06 | 2023-11-25 | To Do | Sarah Johnson | 0
Team Hiring Plan | 2023-11-26 | 2023-12-15 | To Do | Mike Brown | 0
Pitch Deck Creation | 2023-12-16 | 2024-01-15 | To Do | Lisa White | 0
Launch Preparation & Testing | 2024-01-16 | 2024-02-15 | To Do | All Team Members | 0