## Worksheet
Startup Planning - Time Tracker Dashboard
Monitor project progress and time allocation across key initiatives
Project | Task | Assigned To | Start Date | End Date | Budgeted Hours | Actual Hours | Status | Last Updated
Product Development | UI/UX Design Phase 1 | Sarah Johnson | 2024-03-05 | 2024-03-15 | 80 | 76 | Active | 2024-03-14 14:32
Market Research | Cust. Feedback Analysis | James Wilson | 2024-03-07 | 2024-03-18 | 65 | 59 | Active | 2024-03-13 17:18
Fundraising | VC Pitch Deck Revamp | Lisa Chen | 2024-03-06 | 2024-03-19 | 75 | 81 | Pending Review | 2024-03-14 09:25
Team Hiring | Frontend Developer Role | Marcus Reed | 2024-03-01 | 2024-03-31 | 95 | 87 | Active | 2024-03-14 15:47
Product Development | API Integration Testing | Alex Turner | 2024-03-08 | 2024-03-16 | 68 | 55 | Completed | 2024-03-13 19:05
Total Hours: |  |  |  |  | 383 | 358
Export to CSVPrint ReportAdd New Task