## Startup Planning - Time Tracker
Startup Planning - Time Tracker
Project Phase | Task Description | Start Date | End Date | Assigned To | Status | Total Hours Spent
Research & Ideation | Market Analysis and Customer Segmentation | 2025-01-10 | 2025-01-31 | Alice Johnson | In Progress | 48.5
Business Model Design | Develop MVP Framework and Revenue Streams | 2025-02-01 | 2025-02-14 | Michael Chen | To Do | 0
Funding Strategy | Pitch Deck Development & Investor Outreach Plan | 2025-02-15 | 2025-03-01 | Sarah Williams | Not Started | 0
Product Development | UI/UX Design and Wireframing Phase 1 | 2025-03-02 | 2025-03-18 | Daniel Rodriguez | In Progress | 67.8
Team Building | Hire Core Development Team (Frontend & Backend) | 2025-03-19 | 2025-04-15 | Linda Thompson | To Do | 0
Testing & QA | User Acceptance Testing (UAT) - Alpha Release | 2025-04-16 | 2025-05-14 | Ryan Foster | Not Started | 0
Go-to-Market Planning | Create Launch Strategy & Marketing Campaigns | 2025-05-15 | 2025-06-30 | Maria Garcia | To Do | 0
Total Time Spent (All Tasks) | [5 empty] | 116.3
Last Updated:April 5, 2025 ¦ Prepared by: Startup Planning Team