## Worksheet
Startup Planning - Time Tracker (Multi Page)
Track your project time across multiple phases and team members
Phase 1: Ideation & Planning
Task | Assigned To | Start Date | End Date | Status | Hours Logged (Est.)
Create business concept document | Alice Johnson | 2024-01-05 | 2024-01-15 | In Progress | 8.5
Conduct market research & competitor analysis | Robert Chen | 2024-01-06 | 2024-01-18 | Pending | 15.3
Develop initial pitch deck (Version 1) | Sarah Williams | 2024-01-07 | 2024-01-16 | In Progress | 5.8
Phase 2: Product Development
Task | Assigned To | Start Date | End Date | Status | Hours Logged (Est.)
User interface design (wireframes) | Jamal Patel | 2024-01-18 | 2024-01-31 | In Progress | 36.5
Backend architecture design & database schema | Laura Gomez | 2024-01-19 | 2024-01-31 | Pending | 8.7
Create MVP feature set specification document | Alice Johnson | 2024-01-25 | 2024-01-31 | Pending | 5.6
Phase 3: Testing & Pre-Launch
Task | Assigned To | Start Date | End Date | Status | Hours Logged (Est.)
User acceptance testing (UAT) | Sarah Williams | 2024-02-01 | 2024-02-15 | Pending | 16.3
Performance & load testing setup and execution | Robert Chen | 2024-02-03 | 2024-02-15 | Pending | 18.9
Create launch marketing plan & assets | Jamal Patel | 2024-01-30 | 2024-02-16 | Pending | 7.5
Phase 4: Post-Launch & Iteration
Task | Assigned To | Start Date | End Date | Status | Hours Logged (Est.)
Gather user feedback from launch phase | Alice Johnson | 2024-02-17 | 2024-03-15 | Pending | 19.8
Analyze usage metrics & KPIs | Laura Gomez | 2024-02-18 | 2024-03-17 | Pending | 16.5
Plan and implement first major feature update | Sarah Williams | 2024-03-01 | 2024-03-31 | Pending | 78.4
Project Summary & Performance Metrics
Category | Total Hours (Est.) | Actual Hours Logged | Team Member Count
Total Project Duration | 196.2 hours | - | 5 team members
Average Hours Per Team Member | 39.2 hours | - | -
Total Tasks Completed (of 15) | 0/15 | - | -