## Worksheet
Startup Planning - Time Tracker - Planning View
Week | Task/Activity | Owner | Estimated Hours | Status | Budget Allocated ($)
Week 1 | Market Research & Validation | Team Lead | 8 | In Progress | $500
| Week 2 | Competitor Analysis | Market Analyst | 6 | In Progress | $400
|  | Week 3 | Define Product MVP Features | Product Manager | 10 | Pending | $800
|  |  | Week 4 | Build Wireframes & Prototypes | UX Designer | 12 | Pending | $900
Week 5 | Develop MVP Core Features (Frontend) |  |  | Frontend Dev | 20 | Pending | $1,500
| Week 6 |  |  | Develop MVP Core Features (Backend) | Backend Dev | 22 | Pending | $1,700
|  |  | Week 7 | UI/UX Finalization & Testing | UX Lead | 8 | Pending | $600
|  | Week 8 |  | Internal Testing & Bug Fixes | QA Team | 15 | Pending | $1,200
Week 9 |  |  |  | Prepare Launch Plan & Marketing Assets | Marketing Lead | 12 | Pending | $800
| Week 10 |  | Finalize Launch Timeline & Roadmap | CEO | 6 | Pending | $500
|  |  | Post-Launch Review & Planning | Team Lead | 8 | Pending | $600
Total (All Weeks) |  |  | 159 hours |  | $10,000