## Worksheet
Startup Planning - Time Tracker (Summary View)
Project Phase | Task Description | Assigned To | Start Date | End Date | Total Hours (Planned) | Total Hours (Actual)
Total Time Summary: |  |  |  |  | 120.5 | 117.3
Research & Ideation | Market Analysis and Competitor Research | Jane Doe | 2024-04-01 | 2024-04-15 | 35 | 38.5
Product Development | User Interface Design and Prototyping | John Smith | 2024-04-16 | 2024-05-15 | 45 | 39.8
Business Modeling | Create Financial Projections and Funding Strategy | Amy Johnson | 2024-05-16 | 2024-06-15 | 30 | 38.9
Marketing & Launch Preparation | Develop Marketing Plan and Pre-Launch Campaigns | Daniel Lee | 2024-06-16 | 2024-07-15 | 15.5 | 38.9
Final Review & Launch Readiness | Team Finalization and Go-Live Preparation | Lisa Wang | 2024-07-16 | 2024-07-31 | 5 | 4.8
Performance Overview
Planned Hours:120.5 ¦Actual Hours:117.3 ¦Variance:-3.2 hours
Note: The project is slightly under schedule with a small variance in time spent.
Generated on April 5, 2024 ¦ Startup Planning - Time Tracker (Summary View)