## Worksheet
Startup Planning - Time Tracker
Tracking View ¦ Project Duration: January 2024 - December 2024
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Progress (%)
TASK-001 | Market Research & Competitor Analysis | Jane Doe | 2024-01-05 | 2024-01-31 | Ongoing | 85%
TASK-002 | Business Model Development | John Smith | 2024-01-15 | 2024-02-15 | Ongoing | 67%
TASK-003 | Prototype Design & UI/UX Mockups | Alex Johnson | 2024-01-20 | 2024-03-15 | Completed | 100%
TASK-004 | Initial Funding Pitch Deck Creation | Lisa Brown | 2024-02-15 | 2024-03-15 | Delayed | 45%
TASK-005 | Legal Structure & IP Registration | Robert Lee | 2024-03-01 | 2024-04-30 | Ongoing | 78%
TASK-006 | Technical Architecture Setup | Maria Garcia | 2024-03-15 | 2024-05-31 | Ongoing | 60%
TASK-007 | Alpha Testing & Feedback Collection | David Chen | 2024-05-15 | 2024-06-30 | Delayed | 35%
TASK-008 | Seed Funding Round Preparation | Sarah Wilson | 2024-06-15 | 2024-08-15 | Ongoing | 70%
TASK-009 | Full Product Launch Planning | Chris Taylor | 2024-08-15 | 2024-11-30 | Ongoing | 55%
TASK-010 | Post-Launch Monitoring & Iteration | Amanda Patel | 2024-12-01 | 2025-03-31 | Completed | 100%