## Worksheet
Startup Planning - Annual To-Do List
Quarter | Task Title | Description | Status | Responsible Team/Person | Due Date
Q1 - Jan - Mar | Market Research & Validation | Conduct surveys, interviews, and competitor analysis to validate product-market fit. | In Progress | Product Team | 2024-01-31
| Build MVP Foundation | Create core features for Minimum Viable Product (MVP). | In Progress | Engineering Team | 2024-02-15
| Define Target Audience Persona | Develop detailed user personas based on research findings. | In Progress | Marketing Team | 2024-01-28
Q1 - Jan - Mar | Secure Seed Funding | Prepare pitch deck, financial model, and investor outreach plan. | Not Started | Funding Team | 2024-03-15
| Q1 - Jan - Mar | Set Up Legal & Compliance Structure | Register company, set up bank account, finalize contracts. | In Progress | Legal & Admin Team | 2024-03-10
|  | Q2 - Apr - Jun | Launch MVP Beta Test | Deploy MVP to 50 early adopters for feedback. | Not Started | Product & QA Team | 2024-05-15
Q2 - Apr - Jun |  |  | Refine Product Based on Feedback | Implement top 5 user suggestions from beta testers. | Not Started | Engineering & UX Team | 2024-06-10
| Q2 - Apr - Jun |  | Develop Go-to-Market Strategy | Create content, pricing model, and initial outreach campaign. | Not Started | Marketing & Sales Team | 2024-06-15
|  | Q2 - Apr - Jun | Recruit First 5 Key Team Members | Fill critical roles in engineering, marketing, and customer support. | Not Started | Hiring Team | 2024-06-30
Q3 - Jul - Sep |  |  | Launch Public Beta Version | Open MVP to wider audience with improved features. | Not Started | Product & Dev Team | 2024-08-15
| Q3 - Jul - Sep |  | Collect User Analytics & Feedback | Track usage patterns, retention, and feature engagement. | Not Started | Data Team | 2024-09-15
|  | Q3 - Jul - Sep | Secure First 100 Paid Customers | Implement onboarding process and targeted campaigns. | Not Started | Sales & Marketing Team | 2024-09-30
Q3 - Jul - Sep |  |  | Evaluate Year 1 Goals & Adjust Roadmap | Review performance against KPIs and refine next year's plan. | Not Started | Leadership Team | 2024-09-30
| Q4 - Oct - Dec |  | Scale Customer Acquisition Efforts | Expand paid marketing and partnerships to grow user base. | Not Started | Marketing Team | 2024-11-30
|  | Q4 - Oct - Dec | Optimize Retention & Support Systems | Implement onboarding flows and improve customer support. | Not Started | Customer Success Team | 2024-11-15
Q4 - Oct - Dec |  |  | Prepare for Year 2 Funding Round | Build financial projections and investor presentation. | Not Started | Funding & Leadership Team | 2024-12-15
| Q4 - Oct - Dec |  | Annual Review & Planning Workshop | Reflect on the year, celebrate wins, and plan Year 2 strategy. | Not Started | All Teams | 2024-12-18
Template generated for Startup Planning – Annual To-Do List • Last updated: January 2024