## Worksheet
Task | Deadline | Assigned To | Status | Priority
Define business concept and value proposition | 2023-10-15 | CEO | In Progress | High
Conduct market research and competitor analysis | 2023-10-20 | Marketing Lead | Completed | Medium
Create detailed business plan and financial projections | 2023-10-25 | CFO | In Progress | High
Develop MVP (Minimum Viable Product) | 2023-11-10 | CTO | Not Started | High
Secure initial funding or investor pitch preparation | 2023-11-15 | CEO & CFO | Not Started | High
Establish legal structure and register company | 2023-10-30 | Legal Advisor | Completed | Medium
Build core team and hire key staff | 2023-11-05 | HR Manager | In Progress | High
Set up office and IT infrastructure | 2023-10-28 | Operations Lead | Completed | Medium
Launch pilot program or beta test | 2023-11-20 | Product Manager | Not Started | High
Develop marketing and branding strategy | 2023-11-05 | Marketing Lead | Completed | Medium