## Worksheet
Startup Planning - To-Do List (Client View)
Task | Priority | Status | Due Date | Assigned To
Define core business idea and value proposition | High | Pending | 2024-05-15 | CEO & Founder
Conduct market research and competitor analysis | High | Pending | 2024-05-20 | Marketing Lead
Create MVP prototype and wireframes | Medium | In Progress | 2024-05-25 | Product Designer
Develop initial pitch deck for investors | High | Pending | 2024-05-18 | CEO & Founder
Secure initial seed funding (target: $100K) | High | Pending | 2024-06-30 | COO & Investor Relations
Register company and legal entity | Medium | In Progress | 2024-05-17 | Legal Counsel
Build basic website and landing page | Medium | In Progress | 2024-05-28 | Web Developer
Establish key partnerships and advisors | Low | Pending | 2024-06-15 | CEO & Founder
Set up CRM and project management tools | Medium | Completed | 2024-05-10 | IT Manager
Finalize team roles and responsibilities matrix | High | Completed | 2024-05-12 | HR Lead & CEO
Startup Planning To-Do List • Client View • Updated as of May 10, 2024