## Worksheet
Startup Planning - Detailed To-Do List
Task ID | Task Description | Category | Priority | Status | Due Date | Assigned To | Notes / Details
🚀 Pre-Startup Phase (Ideation & Validation)
TSK-001 | Define core problem statement and target audience | Ideation | High | Pending | 2024-05-15 | John Doe (Founder) | Validate with 10 customer interviews
TSK-002 | Conduct market research: analyze competitors and trends | Research | High | In Progress | 2024-05-20 | Sarah Lee (Market Analyst) | Use Statista, Crunchbase, and Google Trends
TSK-003 | Create initial business model canvas (BMC) | Strategy | High | Pending | 2024-05-18 | Maria Garcia (Strategy Lead) | Include revenue streams and key activities
🛠️ Product Development Phase
TSK-004 | Build wireframes and UI/UX mockups for MVP | Design | High | In Progress | 2024-05-25 | James Chen (UX Designer) | Use Figma; feedback from 3 stakeholders required
TSK-005 | Develop MVP backend architecture and API endpoints | Engineering | High | Pending | 2024-06-15 | Liam Patel (CTO) | Use Node.js + MongoDB; include authentication module
TSK-006 | Set up CI/CD pipeline with GitHub Actions | DevOps | Medium | Pending | 2024-05-30 | Olivia Smith (DevOps Engineer) | Automated testing and deployment to staging
📣 Marketing & Sales Phase
TSK-007 | Develop brand identity: logo, color palette, voice guidelines | Branding | High | In Progress | 2024-05-18 | Emma Wilson (Creative Director) | Present to founding team by 2024-05-17
TSK-008 | Create landing page with conversion tracking | Marketing | High | Pending | 2024-06-05 | David Kim (Digital Marketer) | Include email capture form and CTA button
TSK-009 | Plan first 3-month customer acquisition strategy | Sales & Marketing | Medium | Pending | 2024-05-28 | Nathan Taylor (Growth Lead) | Include social media, SEO, and referral program
💰 Operations & Finance Phase
TSK-010 | Register business entity and obtain EIN | Legal & Compliance | High | Pending | 2024-05-17 | Grace Brown (Legal Advisor) | File with Secretary of State and IRS
TSK-011 | Create 3-year financial forecast: P&L, cash flow, balance sheet | Finance | High | Pending | 2024-05-31 | Aiden Reed (CFO) | Include assumptions and sensitivity analysis
TSK-012 | Set up accounting system (QuickBooks or Xero) | Finance | Medium | Pending | 2024-05-25 | Sophia Martinez (Accountant) | Configure chart of accounts and bank feeds
👥 Team & Culture Phase
TSK-013 | Define company mission, vision, and values | Culture & Leadership | High | In Progress | 2024-05-16 | John Doe (Founder) | Involve all core team members in workshop
TSK-014 | Hire first 3 full-time employees: CTO, UX Designer, Marketer | Talent Acquisition | High | Pending | 2024-06-10 | Grace Brown (HR Manager) | Post on LinkedIn, AngelList, and job boards
🏁 Final Milestones & Launch Readiness
TSK-015 | Conduct internal MVP beta test with 15 users | Quality Assurance | High | Pending | 2024-06-20 | Liam Patel (CTO) | Collect feedback and fix critical bugs
TSK-016 | Finalize launch plan: press release, social rollout, media outreach | Launch Strategy | High | Pending | 2024-06-30 | Nathan Taylor (Growth Lead) | Coordinate with PR agency and influencers
TSK-017 | Official launch day: go live on website and app stores | Launch Execution | High | Pending | 2024-07-01 | Team Lead (All) | Monitor performance, server load, user onboarding
Template Version: v1.0 ¦ Last Updated: April 5, 2024 ¦ Generated via Startup Planning To-Do List