## Worksheet
Startup Planning - Weekly Planner (Analysis View)
Day | Monday | Tuesday | Wednesday
Key Focus Area | Product Development Milestone Review |  | Market Research & Customer Validation
Goal #1 - Objective: | Finalize MVP feature set | Begin UI/UX prototyping | Analyze customer feedback data
Task / Activity: | Create user story mapping session | Design wireframe for core dashboard | Compile survey results from 100 users
Status: | In Progress | In Progress | In Progress
Metrics (KPIs): | 10 user stories defined | Wireframe draft completed (85%) | 52% positive sentiment rate
Dependencies: | Feedback from Product Team | Design system approval | Data cleaning completed by Analytics Lead
Risk Level: | Medium (Timeline delay possible) | Low (well-defined scope) | High (data quality concerns)
Notes: | Awaiting input from stakeholders by EOD | Review session scheduled for Thursday | Consider segmenting feedback by age group
Action Items: | Share backlog with dev team on Friday | Send mockups to marketing for early testing | Prepare visualization dashboard for review
Owner: | Jane Doe (Product Manager) | Mike Chen (Lead Designer) | Sarah Kim (Data Analyst)
Last Updated:April 5, 2025 ¦Version:Analysis View v1.3