## Worksheet
Startup Planning - Weekly Planner (Client View)
Week of | Monday | Tuesday | Wednesday | Thursday | Friday
Week of May 6, 2024
Project Kickoff | Finalize team roles Status: Complete | Define product vision Status: In Progress | Conduct market research Status: Pending | Draft initial roadmap Status: Pending | Schedule stakeholder meeting Status: Pending
Week of May 13, 2024
Product Development | Review research findings Status: Complete | Develop MVP wireframes Status: In Progress | Begin UX prototyping Status: Pending | Review feedback from design team Status: Pending | Finalize core features list Status: Pending
Week of May 20, 2024
Technical Execution | Implement core backend logic Status: Complete | Set up development environment Status: In Progress | Begin front-end component build Status: Pending | Integrate authentication system Status: Pending | Run first internal test cycle Status: Pending
Week of May 27, 2024
Testing & Feedback | Collect user feedback Status: Complete | Address bug reports Status: In Progress | Run regression testing Status: Pending | Prepare for beta release Status: Pending | Review metrics and KPIs Status: Pending
Week of June 3, 2024
Launch Preparation | Finalize marketing plan Status: Complete | Create launch announcement Status: In Progress | Set up analytics dashboard Status: Pending | Train customer support team Status: Pending | Conduct final system check Status: Pending
Week of June 10, 2024
Go-Live & Review | Deploy to production Status: Complete | Monitor launch performance Status: In Progress | Gather initial user feedback Status: Pending | Conduct post-launch review Status: Pending | Plan next sprint Status: Pending